## Manufacturing_Project_Plan
Task ID | Task Name | Phase | Owner | Start Date | End Date | Duration (Days) | Predecessor | % Complete | Status | Budget ($)
1 | Project Kickoff | Initiation | Project Manager | 2026-03-01 | 2026-03-03 | 3 |  | 100 | Complete | 2000
2 | Requirements Gathering | Planning | Manufacturing Eng. | 2026-03-04 | 2026-03-10 | 7 | 1 | 100 | Complete | 5000
3 | RFQ Preparation | Planning | Supply Chain | 2026-03-11 | 2026-03-15 | 5 | 2 | 100 | Complete | 3000
4 | Supplier Selection | Execution | Sourcing Manager | 2026-03-16 | 2026-03-25 | 10 | 3 | 80 | In Progress | 15000
5 | PO Release | Execution | Procurement | 2026-03-26 | 2026-03-28 | 3 | 4 | 0 | Not Started | 250000
6 | Equipment Build | Execution | Supplier | 2026-03-29 | 2026-05-15 | 48 | 5 | 0 | Not Started | 0
7 | Factory Acceptance Test (FAT) | Validation | Quality Eng. | 2026-05-16 | 2026-05-20 | 5 | 6 | 0 | Not Started | 7000
8 | Shipment & Installation | Deployment | Field Service | 2026-05-25 | 2026-06-05 | 12 | 7 | 0 | Not Started | 12000
9 | Site Acceptance Test (SAT) | Validation | Quality Eng. | 2026-06-06 | 2026-06-10 | 5 | 8 | 0 | Not Started | 5000
10 | Project Closeout | Closure | Project Manager | 2026-06-11 | 2026-06-15 | 5 | 9 | 0 | Not Started | 3000